## Project Plan
Sample Gantt Chart: "Business Volunteer for the Arts Project"
[8 empty] | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun
| Task |  |  | Dep. | Start | Days | Finish | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
1 | Get Organized
2 |  | Create project plan |  |  | 2002-12-16 | 14 | 2002-12-30 | bar: Jan 1
3 |  | Have kickoff meeting |  | 2 | 2002-12-31 | 1 | 2003-01-01 | bar: Jan 1
4 | Volunteer Recruitment
5 |  | Get contact information for corporate contacts |  |  | 2003-01-02 | 10 | 2003-01-12 | bar: Jan 1 to Jan 2
6 |  | Create application packet and send to corporate contacts |  | 5,12 | 2003-01-13 | 60 | 2003-03-14 | bar: Jan 3 to Mar 10
7 |  | Read applications and schedule interviews |  | 6 | 2003-03-15 | 7 | 2003-03-22 | bar: Mar 11
8 |  | Conduct interviews |  | 7 | 2003-03-23 | 5 | 2003-03-28 | bar: Mar 12
9 |  | Accept or deny and confirm enrollment |  | 8 | 2003-03-29 | 5 | 2003-04-03 | bar: Apr 13
10 |  | Enter volunteer information into database |  | 9 | 2003-04-04 | 5 | 2003-04-09 | bar: Apr 14
11 | Volunteer Training
12 |  | Set training dates and reserve meeting rooms |  | 3, =25 | 2003-01-02 | 1 | 2003-01-12 | bar: Jan 1 to Jan 2
13 |  | Amend training design |  |  | 2003-03-15 | 14 | 2003-03-29 | bar: Mar 11 to Mar 12
14 |  | Recruit and schedule trainers |  | 12 | 2003-03-17 | 14 | 2003-03-31 | bar: Mar 11 to Mar 12
15 |  | Create training materials |  | 9 | 2003-03-30 | 30 | 2003-04-29 | bar: Apr 13 to Apr 16
16 |  | Hold volunteer training sessions |  | 15, 17 | 2003-04-30 | 7 | 2003-05-07 | bar: May 17
18 | Arts Organization Recruitment
19 |  | Create and send out announcement |  | 12 | 2003-01-13 | 60 | 2003-03-14 | bar: Jan 3 to Mar 11
20 |  | Read applications and schedule needs assessments |  | 19 | 2003-03-15 | 7 | 2003-03-22 | bar: Mar 12
21 |  | Conduct and write up needs assessments |  | 20 | 2003-03-23 | 21 | 2003-04-13 | bar: Apr 13 to Apr 15
22 |  | Enter info on arts organizations into database |  | 21 | 2003-04-14 | 7 | 2003-04-21 | bar: Apr 15
17 |  | Create arts organization profiles for volunteers to choose from |  | 16 | 2003-04-22 | 7 | 2003-04-29 | bar: Apr 16
24 | Arts Organization Orientation
25 |  | Reserve meeting rooms |  | =12 | 2003-01-02 | 1 | 2003-01-03 | bar: Jan 1
26 |  | Amend training design |  |  | 2003-03-15 | 14 | 2003-03-29 | bar: Mar 11 to Mar 12
27 |  | Recruit and schedule trainers |  | 12 | 2003-03-17 | 14 | 2003-03-31 | bar: Mar 11 to Mar 12
28 |  | Create training materials |  |  | 2003-03-30 | 30 | 2003-04-29 | bar: Apr 13 to Apr 16
23 |  | Hold arts organization orientations and assess eligibility |  | 28 | 2003-04-30 | 7 | 2003-05-07 | bar: May 17
29 | Matches
30 |  | Volunteers complete preference sheets |  | =16, 17, 22 | 2003-04-30 | 7 | 2003-05-07 | bar: May 17
31 |  | Select matches |  | 23,30 | 2003-05-08 | 1 | 2003-05-09 | bar: May 18
32 |  | Call volunteers and organizations and schedule meetings |  | 31 | 2003-05-10 | 7 | 2003-05-17 | bar: May 18
33 |  | Conduct match meetings and write up contracts |  | 32 | 2003-05-17 | 14 | 2003-05-31 | bar: May 19 to May 20
34 |  | Enter information on match into database |  | 33 | 2003-06-01 | 7 | 2003-06-08 | bar: Jun 21
Use this tool to create an overview of your project.
Step 1: Write out the key tasks and the "critical path" on another piece of paper
Step 2: Group the tasks in a logical way on the spreadsheet
Step 3: Note any dependencies in the "Dep." column (e.g., Task 6 cannot start until Tasks 5 and 12 are completed)
Step 4: Assign durations for each task. This plan assigns 7 days for a five-day work-week.
Step 5: Working backwards from the date by which the project must be finished (or working forward from your starting date), plug in the appropriate formulas
(e.g., the start date for Task 8 = the finish date for Task 7 plus 1). In this sample, all fields other than the one in yellow are calculated fields.
Step 6: After checking the logic of the plan, create the Gantt chart manually
You can change the formulas in the start and finish fields to adjust the relationships between tasks. The greyed out column with the heading "Dep." (for "dependencies" indicates the precedent tasks; an equals sign indicates that the start date is the same as the indicated row).

## Project Budget
Line Item | Cost/Unit | # of Units | Cost | Notes
Volunteer Recruitment
Copying - recruitment | 0.05 | 500 | 25 | 100 5-page packets
Copying - followup | 0.05 | 200 | 10 | 40 5-page packets
Postage | 0.75 | 140 | 105
Staff time * | 17.3 | 20 | 346
Volunteer Applications
Staff time | 17.3 | 50 | 865
Volunteer Training
Copying | 0.05 | 750 | 37.5 | 25 30-page packets
Food | 10 | 100 | 1000 | 25 meals x 4 nights
Room rental | 100 | 4 | 400 | 4 nights
Staff time - Program Mgr | 17.3 | 60 | 1038
Staff time - ED | 28.85 | 16 | 461.6
Arts Organization Recruitment
Copying - recruitment | 0.05 | 10 | 0.5 | 10 1-page packets
Copying - followup | 0.05 | 300 | 15 | 30 10-page packets
Postage - followup | 0.34 | 10 | 3.4 | 10 packets
Postage - recruitment | 0.75 | 30 | 22.5 | 30 packets
Staff time | 17.3 | 10 | 173
Volunteer Applications
Travel | 20 | 20 | 400 | 20 trips @ $20 (mileage + parking)
Staff time | 17.3 | 100 | 400
Total |  |  | 5302.5
* Hourly rate based on an annual salary of $29,000 for 2000 hours of work, plus 20% for benefits

## Issues List
ID | Priority | Issue | Solution/Information | Status
1
2
3
4
4
5
6
7
8
9

## Responsibility Matrix - Roles
P = Carries out work | I = Gives input about work
A = Approves work | R = Reviews work (oversight role)
Tasks | Sponsor | Project Manager | Consultant | Advisory Committee
VOLUNTEER RECRUITMENT
Gather list of corporate volunteer coordinators. |  | P |  | I
Compile fact sheet, cover letter, and applications, and mail to corporate contacts. | R | I, A | P | I
Send information to the Volunteer Centers. |  |  | P
Write PSA announcement and mail. | A | I | P
Answer phone inquiries and send packets. |  | P
VOLUNTEER APPLICATIONS
Read incoming applications, and contact to schedule interview. |  | P
Flag likely problem areas and develop list of key questions. |  | P
Conduct interviews (35 0.5 - 0.75 hour sessions). |  | P | P
Enter information volunteers into database. |  | P
VOLUNTEER TRAINING
Review timing of workshops, special events, and volunteer training schedule for the year. |  | P | I
Determine best possible dates and reserve meeting rooms. | A | P

## Responsibility Matrix-Volunteer
Who | Duty | Station | Time | Items Needed/Details
Pardis | CompassPoint Display and Publications SET-UP | Exhibitor’s Hall | 7AM or earlier Plus the day before. | Will need to prepare the display, assemble and pack the materials in the days before the conference.
Robin | CompassPoint Display and Publications SET-UP | Exhibitor’s Hall | 7AM or earlier Plus the day before. | Will need to prepare the display, assemble and pack the materials in the days before the conference.
Pardis | CompassPoint Display Booth Attendant | Exhibitor’s Hall - bookstore | 8:00 AM – 10:45 AM | Must be friendly and willing to say hello and start conversations with booth visitors.
Peter | CompassPoint Display Booth Attendant | Booth | 8:00 AM – 10:45 AM | Must be friendly and willing to say hello and start conversations with booth visitors.
Jeanne | CompassPoint Display Booth Attendant | display | 10:45 AM – 12:00 PM | Must be friendly and willing to say hello and start conversations with booth visitors.
Robin | CompassPoint Display Booth Attendant | Exhibitor’s Hall | 11 - 12:15 | Must be friendly and willing to say hello and start conversations with booth visitors.
Barrett | CompassPoint Display Booth Attendant | Exhibitor’s Hall - bookstore | 12:00 PM – 2:00 PM | Must be friendly and willing to say hello and start conversations with booth visitors.

## Gather Information
Who | Questions
Agency Name/Contact | Current arts mgt services in the East Bay? | Publications that go to East Bay arts agencies? | Mailing lists for East Bay arts agencies? | Common arts organization mgt concerns?